## Sheet1
assessment_criteria_id | assessment_criteria | data_points_used | formula | weightage | thresholds_good | thresholds_satisfactory | thresholds_needs_improvement
PM-AC-001 | DevCo Schedule Performance Index (SPI) | Planned Value (PV) (No.), Earned Value (EV) (No.) | Earned Value (EV) / Planned Value (PV) | 0.7 | >1 | 0.85-1 | <0.85
PM-AC-002 | % milestone achievement in accordance with the approved business plan | No. of planned milestones (No.), No. of milestones achieved on time (No.) | No. of milestones achieved on time/ No. of planned milestones | 0.3 | >70% | 50-70% | <50%
PM-AC-003 | % of projects with approved change requests in design phase since inception with time impact of more than 1 month | Total number of projects in design phase (No.), Number of projects with approved change requests in design phase since inception with time impact of more than 1 month (No.) | Number of projects with approved change requests in design phase since inception with time impact of more than 1 month / Total number of projects in design phase | 0.4 | <30% | 30-70% | >70%
PM-AC-004 | % of projects with approved change requests in construction phase since inception with time impact of more than 4 months | Total number of projects in construction phase (No.), Number of projects with approved change requests in construction phase since inception with time impact of more than 4 months (No.) | Number of projects with approved change requests in construction phase since inception with time impact of more than 4 months / Total number of projects in construction phase | 0.4 | <30% | 30-70% | >70%
PM-AC-005 | % of projects with approved schedule extension | No. of Approved EOTs (No.), No. of projects with schedule extension (design stage) (No.), No. of projects with schedule extension (construction stage) (No.) | (Number of Projects with Approved Schedule Extension)/Total Number of Projects) | 0.2 | <20% | 20-40% | >40%